## CUSTOMER POCs-EM-83
ORGANIZATION NAME : | EMAM, Inc
LOGIN NAME : | Rincy Abraham
PROJECT NAME : | CUSTOMER POCs
PROJECT ID : | EM-83
REPORT TAKEN ON : | 1 November 2023 09:23:00 AM
REPORT FOR : | 11-01-2022 To 11-01-2023
For Whom : | All Users
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
09-25-2023 | ETV_Install Net X Convert | CP1-T31 | 01:00 | Shaludas MK | Billable | install netxproxy and tested | Shaludas MK | 1 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
09-24-2023 | ETV_Troubleshoot Workflow configurations | CP1-T30 | 01:00 | Shaludas MK | Billable | Fixed and tested workflow notification emails . | Shaludas MK | 1 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
06-29-2023 | ETV_Troubleshoot Proxy import from S3 (after upgrade) | CP1-T26 | 02:00 | Shaludas MK | Billable | We updated ETV to 5.4.4.3_26JUN2023, which fixed a proxy import issue at their corporate headquarters. But we continue to experience import errors in their branch office. | Shaludas MK | 2 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
06-26-2023 | ETV_patch update to 5.4.4.3_26JUN2023 | CP1-T27 | 00:30 | Shaludas MK | Billable | updated 5.4.4.3_26JUN2023 | Shaludas MK | 0.5 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
06-26-2023 | ETV_Meeting_Call with AWS team on proxy import issue using AWS SDK | CP1-T28 | 01:00 | Shaludas MK | Billable | call with AWS team showed the screen grabs of the error we took from the workstation explained how import works using AWS SDK also showed successful import of assets in ETV head office workstation | Shaludas MK | 1 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
06-24-2023 | ETV_Upgrade eMAM to 5.4.4 | CP1-T25 | 02:00 | Prasanth KS | Billable | eMAM upgraded to 5.4.4.1 and did the basic testing found its working fine. | Prasanth KS | 2 | prasanth@emamsolutions.com | Employee | task | POC | None | Execution |  | -
06-16-2023 | ETV_Troubleshooting_upload & eFeeder issues | CP1-T24 | 02:24 | Alex Baby | Billable | Upon investigating the client machine's network settings, I found that they have both a 1 Gbps and a 100 Mbps connection. Currently, the file transfer is taking place through the 100 Mbps connection, and they need to switch to the 1 Gbps connection for faster speeds. Answered customer queries via Anydesk | Alex Baby | 2.4 | alex@emamsolutions.com | Manager | task | POC | None | Execution |  | -
06-16-2023 | ETV_Troubleshooting_upload & eFeeder issues | CP1-T24 | 00:08 | Alex Baby | Billable | They are disabling the network during the file transfer from eFeeder. As of now there is no resume option available. | Alex Baby | 0.133 | alex@emamsolutions.com | Manager | task | POC | None | Execution | 04:07 AM - 04:15 AM | -
04-26-2023 | ETV_Demo_Proxy Edit Workflow | CP1-T22 | 01:00 | Rincy Abraham | Non Billable | Shalu demonstrated Proxy edit workflow using Premiere along with CC workflow. They agreed to test it for 2 more days and come back with feedback this Friday. | Rincy Abraham | 1 | rincy@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
04-18-2023 | ETV_Update till patch_5.3.13.1.2_17APR2023 | CP1-T20 | 02:00 | Shaludas MK | Billable | - | Shaludas MK | 2 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
04-18-2023 | ETV_Configurations for Proxy Edit workflow | CP1-T23 | 00:30 | Shaludas MK | Billable | after patch updated changed the cloud config . Now the proxies will be uploaded to S3 after ingest | Shaludas MK | 0.5 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-31-2023 | ETV_Asisitance with Feeder Instalation and fileupload | CP1-T19 | 02:00 | Shaludas MK | Non Billable | eMAM POC server have 2 IP address 10.10.10.155 & 172.30.41.230. No specific IP was listed by ETV in eMAM install questionnaire , so Implementation team have configured the system with the IP address (10.10.10.155) which has gateway configured. But now they are trying to access the eMAM using the other IP address (172.30.41.230) . So now we must reconfigure the eMAM system with hostname or FQDN | Shaludas MK | 2 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-28-2023 | ETV_Re configure eMAM system using host name | CP1-T18 | 02:00 | Shaludas MK | Billable | - | Shaludas MK | 2 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-21-2023 | ETV- Workflow configuration assistance | CP1-T17 | 04:00 | Shaludas MK | Billable | ETV Workflow - POC testing steps 1. Production house (PH) logs uses eFeeder to upload RAW files to eMAM under the permitted category. 2. A notification goes out to Ravi (ravikumar.k@etv.co.in) 3. Proxy goes to AWS (for now local storage, until we fix the code), Original in ETV storage. 4. Now production house logs into eMAM Panel in Adobe Premiere, finds the raw footage, imports it to Pr (Proxy, Localise) and starts edit. 5. Once edit is complete, they export the project to eMAM with a low res version of sequence. 6. Here a notification to ETV is required - email. 7. ETV team runs a Content Check on the sequence. 8. ETV team puts in markers, annotations, subclips, and fails the CC. Change CC status to fail. 9. An email goes out to PH (prkraju@etv.co.in) 10. PH makes changes, adds a local graphic and exports a new version / or checks in the new project version to eMAM 11. ETV team gets an email - (ravikumar.k@etv.co.in) 12. ETV team reviews and suggests more changes, put in comments and use button - CC QC FAIL? 13. An email goes out to PH (prkraju@etv.co.in) with comments, asset details etc…. 14. PH makes changes and submits another version - project or asset 15. ETV team agains gets an email. 16. ETV passes the asset and changes CC Status to Pass. Again a button CC QC PASS, it updates metadata and sends an email to Ravi (eventually this email will go to PH and respective ETV person for DI? 17. Next, ETV opens Pr, and uses eMAM panel to import the project. Localise with Originals. 18. ETV saves the project locally on same machine which runs Da Vinci Resolve. 19. ETV exports the project from Premiere using FCP Export XML option. 20. ETV now imports the project in Da Vinci using import Timeline, this imports the Adobe project sequence and media is also automatically connected because it is local on the machine. 21. When Da Vinci Resolve finishes, it sends a final output file to eMAM watch folder / ingest using feeder / director. 22. This file is now ready for QC in eMAM. 23. Send to QC button on eMAM will send this file to a designated hot folder for QC system | Shaludas MK | 4 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-20-2023 | ETV- Workflow configuration assistance | CP1-T17 | 04:00 | Shaludas MK | Billable | installed and configured eMAM premiere panel in 3 worksations and demonstrated the workflow if proxy exist only in cloud then we are not able to import , they depends on proxy editing For now have created another storage profile with no cloud configured Issue with SMTP, worked with Enter10 IT team Configured DB mailer | Shaludas MK | 4 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-09-2023 | ETV- eMAM Demo/Training | CP1-T13 | 02:45 | Shaludas MK | Billable | Superadmi training | Shaludas MK | 2.75 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-02-2023 | ETV- Meetings | CP1-T12 | 01:00 | Shaludas MK | Billable | system demo | Shaludas MK | 1 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-02-2023 | ETV- eMAM Demo/Training | CP1-T13 | 02:45 | Rincy Abraham | Non Billable | Super Admin training- by Shaludas Director training- Rincy abraham | Rincy Abraham | 2.75 | rincy@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
02-23-2023 | ETV- Configurations? | CP1-T6 | 00:30 | Shaludas MK | Non Billable | Call with Devesh regarding proxy bucket configuration . The permission to list all buckets has been assigned for time. Did the cloud configuration | Shaludas MK | 0.5 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
02-20-2023 | ETV- Configurations? | CP1-T6 | 00:30 | Shaludas MK | Non Billable | Configuration | Shaludas MK | 0.5 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
02-15-2023 | ETV-Update patch eMAM 5.3 Sprints - 5.3.13_10FEB2023 | CP1-T9 | 00:45 | Rijo Simon | Non Billable | Upgraded the system to 5.3.13. Collected information from the server and updated the notebook. | Rijo Simon | 0.75 | rijo@emamsolutions.com | Employee | task | POC | None | Execution | 11:30 AM - 12:15 PM | -
02-10-2023 | ETV- Configurations? | CP1-T6 | 00:30 | Shaludas MK | Non Billable | Call with Devesh and Ravi regarding Bucket creation and permission | Shaludas MK | 0.5 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
02-08-2023 | ETV-Update patch till 5.3.12.13_06FEB2023 | CP1-T8 | 02:30 | Elvin Paul | Non Billable | Downloaded the 5.3 setup and patches. Patched the system from 5.3 to 5.3.12.13 | Elvin Paul | 2.5 | elvin@emamsolutions.com | Employee | task | POC | None | Execution |  | -
02-07-2023 | ETV- Installation & Apply License? | CP1-T4 | 02:00 | Prasanth KS | Billable | - | Prasanth KS | 2 | prasanth@emamsolutions.com | Employee | task | POC | None | Execution |  | -
02-07-2023 | ETV-Update patches to latest? | CP1-T5 | 02:00 | Elvin Paul | Billable | Patched the system to 5.3.12.13 | Elvin Paul | 2 | elvin@emamsolutions.com | Employee | task | POC | None | Execution |  | -
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 40:47 |  |  |  |  | 40.783

## vineetha raj k
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 00:00 |  |  |  |  | 0

## rincy abraham
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
04-26-2023 | ETV_Demo_Proxy Edit Workflow | CP1-T22 | 01:00 | Rincy Abraham | Non Billable | Shalu demonstrated Proxy edit workflow using Premiere along with CC workflow. They agreed to test it for 2 more days and come back with feedback this Friday. | Rincy Abraham | 1 | rincy@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-02-2023 | ETV- eMAM Demo/Training | CP1-T13 | 02:45 | Rincy Abraham | Non Billable | Super Admin training- by Shaludas Director training- Rincy abraham | Rincy Abraham | 2.75 | rincy@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 03:45 |  |  |  |  | 3.75

## anand dua
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 00:00 |  |  |  |  | 0

## emily neal
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 00:00 |  |  |  |  | 0

## prasanth ks
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
06-24-2023 | ETV_Upgrade eMAM to 5.4.4 | CP1-T25 | 02:00 | Prasanth KS | Billable | eMAM upgraded to 5.4.4.1 and did the basic testing found its working fine. | Prasanth KS | 2 | prasanth@emamsolutions.com | Employee | task | POC | None | Execution |  | -
02-07-2023 | ETV- Installation & Apply License? | CP1-T4 | 02:00 | Prasanth KS | Billable | - | Prasanth KS | 2 | prasanth@emamsolutions.com | Employee | task | POC | None | Execution |  | -
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 04:00 |  |  |  |  | 4

## anoop thomas
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 00:00 |  |  |  |  | 0

## chuck buelow
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 00:00 |  |  |  |  | 0

## aravind
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 00:00 |  |  |  |  | 0

## sonny luyun
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 00:00 |  |  |  |  | 0

## david miller
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 00:00 |  |  |  |  | 0

## elvin paul
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
02-08-2023 | ETV-Update patch till 5.3.12.13_06FEB2023 | CP1-T8 | 02:30 | Elvin Paul | Non Billable | Downloaded the 5.3 setup and patches. Patched the system from 5.3 to 5.3.12.13 | Elvin Paul | 2.5 | elvin@emamsolutions.com | Employee | task | POC | None | Execution |  | -
02-07-2023 | ETV-Update patches to latest? | CP1-T5 | 02:00 | Elvin Paul | Billable | Patched the system to 5.3.12.13 | Elvin Paul | 2 | elvin@emamsolutions.com | Employee | task | POC | None | Execution |  | -
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 04:30 |  |  |  |  | 4.5

## shaludas mk
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
09-25-2023 | ETV_Install Net X Convert | CP1-T31 | 01:00 | Shaludas MK | Billable | install netxproxy and tested | Shaludas MK | 1 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
09-24-2023 | ETV_Troubleshoot Workflow configurations | CP1-T30 | 01:00 | Shaludas MK | Billable | Fixed and tested workflow notification emails . | Shaludas MK | 1 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
06-29-2023 | ETV_Troubleshoot Proxy import from S3 (after upgrade) | CP1-T26 | 02:00 | Shaludas MK | Billable | We updated ETV to 5.4.4.3_26JUN2023, which fixed a proxy import issue at their corporate headquarters. But we continue to experience import errors in their branch office. | Shaludas MK | 2 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
06-26-2023 | ETV_patch update to 5.4.4.3_26JUN2023 | CP1-T27 | 00:30 | Shaludas MK | Billable | updated 5.4.4.3_26JUN2023 | Shaludas MK | 0.5 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
06-26-2023 | ETV_Meeting_Call with AWS team on proxy import issue using AWS SDK | CP1-T28 | 01:00 | Shaludas MK | Billable | call with AWS team showed the screen grabs of the error we took from the workstation explained how import works using AWS SDK also showed successful import of assets in ETV head office workstation | Shaludas MK | 1 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
04-18-2023 | ETV_Update till patch_5.3.13.1.2_17APR2023 | CP1-T20 | 02:00 | Shaludas MK | Billable | - | Shaludas MK | 2 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
04-18-2023 | ETV_Configurations for Proxy Edit workflow | CP1-T23 | 00:30 | Shaludas MK | Billable | after patch updated changed the cloud config . Now the proxies will be uploaded to S3 after ingest | Shaludas MK | 0.5 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-31-2023 | ETV_Asisitance with Feeder Instalation and fileupload | CP1-T19 | 02:00 | Shaludas MK | Non Billable | eMAM POC server have 2 IP address 10.10.10.155 & 172.30.41.230. No specific IP was listed by ETV in eMAM install questionnaire , so Implementation team have configured the system with the IP address (10.10.10.155) which has gateway configured. But now they are trying to access the eMAM using the other IP address (172.30.41.230) . So now we must reconfigure the eMAM system with hostname or FQDN | Shaludas MK | 2 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-28-2023 | ETV_Re configure eMAM system using host name | CP1-T18 | 02:00 | Shaludas MK | Billable | - | Shaludas MK | 2 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-21-2023 | ETV- Workflow configuration assistance | CP1-T17 | 04:00 | Shaludas MK | Billable | ETV Workflow - POC testing steps 1. Production house (PH) logs uses eFeeder to upload RAW files to eMAM under the permitted category. 2. A notification goes out to Ravi (ravikumar.k@etv.co.in) 3. Proxy goes to AWS (for now local storage, until we fix the code), Original in ETV storage. 4. Now production house logs into eMAM Panel in Adobe Premiere, finds the raw footage, imports it to Pr (Proxy, Localise) and starts edit. 5. Once edit is complete, they export the project to eMAM with a low res version of sequence. 6. Here a notification to ETV is required - email. 7. ETV team runs a Content Check on the sequence. 8. ETV team puts in markers, annotations, subclips, and fails the CC. Change CC status to fail. 9. An email goes out to PH (prkraju@etv.co.in) 10. PH makes changes, adds a local graphic and exports a new version / or checks in the new project version to eMAM 11. ETV team gets an email - (ravikumar.k@etv.co.in) 12. ETV team reviews and suggests more changes, put in comments and use button - CC QC FAIL? 13. An email goes out to PH (prkraju@etv.co.in) with comments, asset details etc…. 14. PH makes changes and submits another version - project or asset 15. ETV team agains gets an email. 16. ETV passes the asset and changes CC Status to Pass. Again a button CC QC PASS, it updates metadata and sends an email to Ravi (eventually this email will go to PH and respective ETV person for DI? 17. Next, ETV opens Pr, and uses eMAM panel to import the project. Localise with Originals. 18. ETV saves the project locally on same machine which runs Da Vinci Resolve. 19. ETV exports the project from Premiere using FCP Export XML option. 20. ETV now imports the project in Da Vinci using import Timeline, this imports the Adobe project sequence and media is also automatically connected because it is local on the machine. 21. When Da Vinci Resolve finishes, it sends a final output file to eMAM watch folder / ingest using feeder / director. 22. This file is now ready for QC in eMAM. 23. Send to QC button on eMAM will send this file to a designated hot folder for QC system | Shaludas MK | 4 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-20-2023 | ETV- Workflow configuration assistance | CP1-T17 | 04:00 | Shaludas MK | Billable | installed and configured eMAM premiere panel in 3 worksations and demonstrated the workflow if proxy exist only in cloud then we are not able to import , they depends on proxy editing For now have created another storage profile with no cloud configured Issue with SMTP, worked with Enter10 IT team Configured DB mailer | Shaludas MK | 4 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-09-2023 | ETV- eMAM Demo/Training | CP1-T13 | 02:45 | Shaludas MK | Billable | Superadmi training | Shaludas MK | 2.75 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
03-02-2023 | ETV- Meetings | CP1-T12 | 01:00 | Shaludas MK | Billable | system demo | Shaludas MK | 1 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
02-23-2023 | ETV- Configurations? | CP1-T6 | 00:30 | Shaludas MK | Non Billable | Call with Devesh regarding proxy bucket configuration . The permission to list all buckets has been assigned for time. Did the cloud configuration | Shaludas MK | 0.5 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
02-20-2023 | ETV- Configurations? | CP1-T6 | 00:30 | Shaludas MK | Non Billable | Configuration | Shaludas MK | 0.5 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
02-10-2023 | ETV- Configurations? | CP1-T6 | 00:30 | Shaludas MK | Non Billable | Call with Devesh and Ravi regarding Bucket creation and permission | Shaludas MK | 0.5 | shaludas@emamsolutions.com | Administrator | task | POC | None | Execution |  | -
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 25:15 |  |  |  |  | 25.25

## rijo simon
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
02-15-2023 | ETV-Update patch eMAM 5.3 Sprints - 5.3.13_10FEB2023 | CP1-T9 | 00:45 | Rijo Simon | Non Billable | Upgraded the system to 5.3.13. Collected information from the server and updated the notebook. | Rijo Simon | 0.75 | rijo@emamsolutions.com | Employee | task | POC | None | Execution | 11:30 AM - 12:15 PM | -
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 00:45 |  |  |  |  | 0.75

## alex baby
Date | Task/General/Issue | Task/Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Task List/Module | From - To | Timer Notes
06-16-2023 | ETV_Troubleshooting_upload & eFeeder issues | CP1-T24 | 02:24 | Alex Baby | Billable | Upon investigating the client machine's network settings, I found that they have both a 1 Gbps and a 100 Mbps connection. Currently, the file transfer is taking place through the 100 Mbps connection, and they need to switch to the 1 Gbps connection for faster speeds. Answered customer queries via Anydesk | Alex Baby | 2.4 | alex@emamsolutions.com | Manager | task | POC | None | Execution |  | -
06-16-2023 | ETV_Troubleshooting_upload & eFeeder issues | CP1-T24 | 00:08 | Alex Baby | Billable | They are disabling the network during the file transfer from eFeeder. As of now there is no resume option available. | Alex Baby | 0.133 | alex@emamsolutions.com | Manager | task | POC | None | Execution | 04:07 AM - 04:15 AM | -
Date | Issue | Issue ID | Daily Log | User | Billing Type | Notes | Added By | Hours(For Calculation) | Owner Mailid | Role | Type | Project Group | milestone | Module | From - To | Timer Notes
|  | Total Log Hours | 02:32 |  |  |  |  | 2.533